## Sheet1
Date | Time | Activity | Group
2021-02-03 | - | Write the project proposal | Proposal
2021-02-04 | 19:37 | Submit the proposal on LMS
2021-02-12 | - | Wrote some requirements | Requirements
2021-02-13 | 1:40 | Wrote the Insurance and purchase methods | -
2021-02-13 | - | Designed home page | UI Design
2021-02-15 | - | Created search page
2021-02-15 | 20:58 | Created 80% of product page (missing user review cards)
2021-02-17 | 14:37 | Finished the product page
2021-02-17 | 15:05 | Improved the home page
2021-02-18 | 18:30 | Created the Git repository | Git Repo
2021-02-24 | 16:13 | Wrote initial requirements | Requirements
2021-02-25 | 20:00 | Created 'Metting' and 'Request' activity diagrams | Domain modelling
2021-02-25 | 22:37 | Wrote the bussniss processes
2021-02-25 | 23:07 | Updated busniss processes (use cases)
2021-02-26 | 15:10 | Updated busniss processes (use cases)
2021-02-26 | 3:51 | Updated insurance process | -
2021-02-27 | 17:34 | Updated busniss processes (use cases) | Domain modelling
2021-02-27 | 17:34 | Wrote first 7 use cases details
2021-02-27 | 21:17 | Updated busniss processes (use cases)
2021-02-27 | 21:17 | Updated use cases details
2021-02-28 | 14:57 | Updated use cases - Grouped edit and remove post
2021-02-28 | 15:02 | Created use cases diagram
2021-02-28 | 19:20 | Created return-tool activity diagram
2021-03-03 | 19:42 | Updated the use cases- refined them and improved the first steps
2021-03-04 | 2:29 | Created new flutter project | Implementaion
2021-03-04 | 17:37 | Wrote first 11 FRs | Requirements
2021-03-04 | 23:15 | Wrote an extra 12 FRs
2021-03-05 | 16:45 | Wrote 9 FRs for main success scenario for use cases 5, 6, and 10
2021-03-05 | 17:07 | Wrote extensions for UC1 | Domain modelling
2021-03-05 | 17:17 | Wrote extensions for UC2
2021-03-05 | 17:35 | Wrote extensions for UC3